HALO CEO SEQUENTIAL EXECUTION PLAN

Day-by-Day, Week-by-Week Guide with Detailed Explanations

Version: 2.0

Date: January 2025

Your Role: Solo Founder & CEO

Goal: $4M Seed Round + Marina Launch in 90 Days

HOW TO USE THIS PLAN

Each task includes:

- WHAT: The specific action to take

- WHY: The strategic reasoning behind it

- OUTPUT: What you should have when complete

- IF STUCK: What to do if you hit obstacles

PHASE 0: FOUNDATION (DAYS 1-14)

Theme: Legal Setup, Team Building, Initial Validation

WHY THIS PHASE MATTERS:

You cannot build Halo without: (1) legal protection for your IP, (2) a technical co-founder or founding engineer, and (3) validation that users actually want this. These 14 days set the foundation for everything that follows. Skip or rush any of these at your peril.

DAY 1: MONDAY - LEGAL ENGAGEMENT & STRUCTURE

Morning (4 hours)

Task 1: Research law firms (Cooley vs Wilson Sonsini vs Gunderson)

WHAT: Spend 1 hour researching these three top-tier startup law firms.

WHY:

- Cooley has specific dating app experience (represented Bumble) - they understand the unique legal landscape of social/matching platforms

- Wilson Sonsini is the gold standard for tech startups in Silicon Valley - they’ve seen every startup situation

- Gunderson is known for being founder-friendly and efficient - good for early-stage cost management

- The right law firm protects you from: patent infringement lawsuits, regulatory violations, founder disputes, and bad investor terms

- Wrong choice = expensive mistakes that kill companies

HOW:

- Visit each firm’s website, read their startup practice descriptions

- Search “[Firm name] dating app” or “[Firm name] AI startup” for relevant experience

- Check Crunchbase for which startups they’ve represented

- Ask your network: “Has anyone worked with [firm]? What was your experience?”

OUTPUT: Decision on which 2 firms to contact (ranked #1 and #2)

IF STUCK: If you can’t decide, contact all 3 and compare their responses. The firm that responds fastest and most thoroughly is often the best choice.

Task 2: Draft outreach email to law firms

WHAT: Write a compelling email to your top 2 law firms.

WHY:

- Law firms are selective about clients - they want high-potential startups that will become long-term relationships

- A well-crafted email signals you’re serious, organized, and worth their time

- Bad emails get ignored or slow responses

- This email sets the tone for the entire relationship

EMAIL TEMPLATE:

Subject: $4M Seed Round - AI-Powered Social Matching Platform

Hi [Partner Name],

I'm the founder of Halo, an AI-powered social operating system where autonomous agents discover compatible people across dating, friendship, and professional domains.

Our agents negotiate matches before humans ever see each other, handling all logistics automatically. We're the first to build true agent-mediated social matching.

Traction:

- Pre-launch with 500+ waitlist signups

- Working prototype with LLM-powered agent negotiation

- 3 provisional patents being filed

- Targeting Marina District launch in SF

We're raising a $4M seed round at $16M post-money and need a law firm with experience in:

- Dating/social platform regulation

- AI/ML IP protection

- Seed-stage venture financing

[Firm name] came highly recommended [specific reason - their work with Bumble, their AI practice, etc.].

Would you have 30 minutes this week to discuss how you could help us?

[Your name]
[LinkedIn profile]
[Phone number]

WHY THIS WORKS:

- Leads with traction (waitlist, prototype) - lawyers want successful clients

- Specific numbers ($4M seed, $16M post) - shows you’ve done your homework

- Lists specific needs - helps them understand scope

- Mentions why you chose them - flatters and shows research

- Clear ask with timeframe - makes it easy to say yes

OUTPUT: 2 emails ready to send

IF STUCK: If you can’t write compelling emails, ask a founder friend to review or hire a copywriter for $200 to draft them.

Task 3: Send emails + follow up with warm intros

WHAT: Send the emails and check LinkedIn for mutual connections.

WHY:

- Warm intros are 10x more effective than cold emails

- Law firms prioritize referred clients

- A warm intro from a portfolio company founder is golden

- Even a weak connection (“we both know Sarah”) helps

HOW TO FIND WARM INTROS:

- Search LinkedIn for the partner’s profile

- Click “Mutual Connections”

- Look for: founders, VCs, other lawyers, accelerator directors

- Message the mutual connection: “Hi [Name], I’m starting a company and looking to connect with [Lawyer] at [Firm]. I saw you’re connected - would you be open to making an intro? Happy to send you a blurb.”

OUTPUT: 2 law firms contacted + any warm intros requested

IF STUCK: If no warm intros available, cold email is fine. Just expect 24-48 hour response time instead of same-day.

Afternoon (4 hours)

Task 4: Create Halo GitHub organization + repos

WHAT: Set up GitHub organization with 3 repositories.

WHY:

- GitHub is where developers live - having a professional setup signals you’re serious

- Separate repos allow parallel development (backend, mobile, agents)

- Version control is non-negotiable for any software project

- Investors will look at your GitHub to assess technical sophistication

- Starting organized prevents technical debt later

REPO STRUCTURE:

- halo-os - Core backend, API, infrastructure

- halo-mobile - React Native iOS/Android app

- halo-agents - LLM agent system, negotiation protocols

WHY 3 REPOS:

- Different deployment cycles (backend deploys daily, mobile weekly, agents continuously)

- Different team members will own each (backend engineer, mobile engineer, ML engineer)

- Clear separation of concerns makes onboarding easier

- Prevents merge conflicts and deployment issues

OUTPUT: GitHub org created with 3 repos, initial README in each

IF STUCK: If you’ve never used GitHub, spend 30 minutes on GitHub’s “Hello World” tutorial first.

Task 5: Document initial product vision in README

WHAT: Write a comprehensive README in the main repo.

WHY:

- This becomes your north star when decisions get hard

- New team members read this first - sets culture and direction

- Forces you to articulate your vision clearly

- Investors will read this to understand your thinking

- You’ll refer back to this when you lose focus

README STRUCTURE:

# Halo

## Autonomous Social Operating System

### Vision

One sentence: What are we building?

### Problem

- 50% of US adults are lonely (Surgeon General 2023)

- Dating apps profit from users staying single

- People don't know what they want in partners

### Solution

- Daemon-per-user architecture

- Agents negotiate matches before humans see anything

- Zero messaging, zero swiping, zero coordination labor

### How It Works

1. User onboarding (10 mins)
2. Agent learns preferences from behavior
3. Agents negotiate with other agents
4. Mutual matches surfaced to users
5. Agents handle scheduling, venue selection

### Technical Architecture

[High-level diagram]

### Business Model

- $30/month subscription

- We win when users find relationships (not when they stay on app)

### Roadmap

- Month 1: Marina launch (200 users)

- Month 3: 3 neighborhoods (1,000 users)

- Month 6: SF-wide (5,000 users)

- Year 1: 10 cities (50,000 users)

### Team

- [Your name] - Founder & CEO

- [Open roles]

### Funding

- Raising $4M seed at $16M post-money

- 18-month runway to Series A

WHY THIS STRUCTURE:

- Vision first - reminds everyone why we’re here

- Problem/Solution - classic investor format

- How It Works - proves you’ve thought through UX

- Technical Architecture - shows technical credibility

- Business Model - addresses the “how do you make money” question

- Roadmap - shows ambitious but realistic thinking

- Team/Funding - transparent about needs

OUTPUT: Comprehensive README committed to GitHub

IF STUCK: If writing is hard, record a 10-minute Loom video explaining Halo, then transcribe it.

Evening (2 hours)

Task 6: Post on personal social media

WHAT: Announce you’re starting something new (without revealing details).

WHY:

- Public commitment increases follow-through

- Your network becomes a source of introductions (investors, hires, users)

- Building in public creates momentum and accountability

- Signals to potential team members that you’re serious

- May surface unexpected connections (“My cousin works at OpenAI!”)

WHAT TO POST:

Excited to share I'm starting something new in the AI + human connection space.

The problem: We're more connected than ever, but lonelier than ever.

The solution: AI agents that actually help people form real relationships.

If you're interested in AI, social products, or just want to follow along, I'll be sharing the journey.

#buildinpublic #AI #startups

WHY THIS WORKS:

- Creates curiosity without revealing secrets (patents pending)

- Frames the problem (loneliness) which everyone understands

- Hints at solution without specifics

- Invites people to follow along

- Hashtags reach beyond your immediate network

OUTPUT: Post published on LinkedIn and Twitter/X

IF STUCK: If you’re uncomfortable with public posts, at minimum tell 10 friends personally. Private commitment is better than no commitment.

DAY 1 SUMMARY & CHECKLIST

What You Should Have:

- ☐ 2 law firms contacted

- ☐ GitHub org with 3 repos

- ☐ Vision README written

- ☐ Public announcement posted

End of Day Check:

CRITICAL QUESTION: Do you have law firm calls scheduled for this week?

IF NO: Send follow-up emails tonight. Law firms are busy - polite persistence wins.

WHY THIS MATTERS: Legal delays cascade. Every day you wait is a day your competitors get ahead. Plus, you cannot raise money or hire without legal entity in place.

DAY 2: TUESDAY - CO-FOUNDER SEARCH BEGINS

Morning (4 hours)

Task 1: Apply to YC Co-Founder Matching

WHAT: Create profile on Y Combinator’s co-founder matching platform.

WHY:

- YC has the highest-quality network of startup-minded engineers

- 100,000+ introductions made, thousands of successful matches

- It’s FREE (unlike CoFoundersLab which charges $30/month)

- YC vets applicants - you’re only matched with serious people

- Even if you don’t find a co-founder, you’ll practice pitching

- Many successful startups found co-founders here (including YC alums)

HOW:

- Go to: cofounder-matching.ycombinator.com

- Create profile (takes 30-45 minutes)

- Be specific about what you’re building and what you need

- Set preferences (location, skills, commitment level)

- Start browsing matches immediately

PROFILE TIPS:

- Be specific: “Building AI-powered social matching” not “working on a startup idea”

- Show traction: “Pre-launch, 500 waitlist, $4M seed in progress”

- Be clear about needs: “Seeking technical co-founder with ML/AI experience”

- Show your credibility: “Former [company] PM, Stanford CS, etc.”

- Use professional photo

WHY SPECIFICITY MATTERS:

- Vague profiles attract vague people

- Specific profiles attract people who are genuinely interested

- Shows you’ve thought through your needs

- Filters out people who aren’t a fit (saves time)

OUTPUT: YC Co-Founder Matching profile live and active

IF STUCK: If application is confusing, search “YC Co-Founder Matching tips” for blog posts from successful matches.

Task 2: Create Wellfound (AngelList) company profile

WHAT: Set up company profile and post first job on Wellfound.

WHY:

- Wellfound (formerly AngelList) is where startup engineers look for jobs

- FREE to post jobs (unlike LinkedIn which charges)

- 8M+ candidates, many specifically want startup experience

- Integrated with investor network (cross-promotion)

- Shows you’re a “real company” to investors and candidates

- You can browse candidate profiles and reach out proactively

HOW:

- Go to wellfound.com

- Create company profile

- Post “Founding Engineer (AI/ML)” job

- Use job description from Appendix A

- Set equity range (1-3%) and salary range ($130-180K)

WHY POST SALARY/EQUITY:

- Transparency attracts serious candidates

- Filters out people who want FAANG salaries

- Sets expectations upfront (no awkward conversations later)

- Shows you understand market rates

- Required by law in some jurisdictions (California)

OUTPUT: Wellfound profile live with job posting

IF STUCK: If writing job description is hard, copy from Appendix A and customize.

Afternoon (4 hours)

Task 3: Write “Founding Engineer (AI/ML)” job description

WHAT: Create compelling job description for your first technical hire.

WHY:

- This is THE MOST IMPORTANT HIRE you’ll make

- A great founding engineer = 10x productivity

- A bad founding engineer = months of delay and technical debt

- Job description attracts (or repels) the right people

- This person may become your co-founder

JOB DESCRIPTION STRUCTURE:

**Founding Engineer (AI/ML)**

*San Francisco | Full-time | $130-180K + 1-3% equity*

**About Halo**

[2-3 sentences on vision]

**The Problem**

- 50% of US adults are lonely

- Dating apps profit from misery

- No one has built agent-mediated matching

**The Solution**

- AI agents negotiate matches automatically

- Zero friction for users

- We win when users find love

**What You'll Do**

- Architect agent system (daemon-per-user)

- Build LLM-powered compatibility prediction

- Design multi-agent negotiation protocols

- Own ML infrastructure end-to-end

- Define technical strategy with founder

- Build engineering team culture

**Must-Have**

- 4+ years software engineering

- 2+ years ML/AI in production

- Python, PyTorch/TensorFlow

- LLM experience (OpenAI, Anthropic)

- Recommendation systems experience

- Vector databases (Pinecone, Weaviate)

- Startup experience or fast shipper

**Nice-to-Have**

- Multi-agent systems

- Dating/social products

- Behavioral data analysis

- Full-stack (React, Node, mobile)

- Published research

- Previous founding engineer

**Compensation**

- Salary: $130-180K (SF seed stage)

- Equity: 1-3% (4-year vest, 1-year cliff)

- Benefits: Health, dental, vision, flexible PTO

**Why Join**

- Category-defining product (first agent-mediated matching)

- Strong scientific foundation (Gottman, attachment theory)

- $4M seed in progress (18-month runway)

- Work directly with founder

- Build the future of human connection

**Apply**

Send resume + 1 paragraph on why you're excited to: [your email]

WHY THIS WORKS:

- Leads with mission (attracts purpose-driven people)

- Problem/Solution shows you understand the space

- Specific responsibilities (not “help build product”)

- Must-have vs nice-to-have filters candidates

- Compensation transparency sets expectations

- “Why Join” sells the opportunity

- Clear application instructions

OUTPUT: Job description ready to post

IF STUCK: If you can’t write this, you don’t understand your technical needs well enough. Spend 2 hours researching similar job postings at AI startups (CrewAI, LangChain, etc.).

Task 4: LinkedIn outreach - Identify 20 ML engineers

WHAT: Create spreadsheet of 20 target candidates at top companies.

WHY:

- Proactive outreach is 10x more effective than waiting for applicants

- Top engineers rarely apply to job postings - they need to be recruited

- LinkedIn allows precise targeting (company, role, skills)

- Personal outreach shows you’re serious

- Even if they’re not interested, they may know someone who is

TARGET COMPANIES (in order of priority):

- OpenAI, Anthropic, Cohere - AI-native, relevant experience

- Hinge, Tinder, Bumble - Dating app ML teams

- Meta, Google, Netflix - Recommendation systems at scale

- Successful AI startups - Jasper, Copy.ai, etc.

- Research labs - Stanford HAI, Berkeley AI Research

WHAT TO LOOK FOR:

- Job title: “ML Engineer”, “AI Engineer”, “Research Engineer”, “Staff Engineer”

- Experience: 4-8 years (senior but not overqualified)

- Skills: Python, PyTorch, LLMs, recommendation systems

- Education: CS/ML degree (BS/MS/PhD)

- Signals: Publications, open-source contributions, conference talks

SPREADSHEET COLUMNS:

| Name | Company | Title | LinkedIn | Why Target | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- |

WHY TRACK IN SPREADSHEET:

- Prevents duplicate outreach

- Helps you remember context

- Shows patterns (many from Meta = focus there)

- Tracks your conversion rates

- Professional way to manage recruiting

OUTPUT: Spreadsheet with 20 targets, ranked by priority

IF STUCK: If you can’t find 20 targets, you’re being too picky. Expand to: fintech companies with ML teams, healthcare AI, autonomous vehicles. Any ML experience is transferable.

Evening (2 hours)

Task 5: Research AI Tinkerers SF next meetup

WHAT: Find date and location of next AI Tinkerers SF meetup.

WHY:

- This is THE event for AI engineers in SF

- Monthly meetups at GitHub HQ with 100-200 attendees

- Free to attend, high-quality networking

- Many people here are looking for their next thing

- Casual environment = easier to build relationships

- Speaking opportunity: You could pitch Halo to the group

HOW:

- Search “AI Tinkerers SF Meetup”

- Join the group on meetup.com

- RSVP to next event

- Block calendar

- Prepare 30-second pitch

WHY IN-PERSON MATTERS:

- Online connections are weak

- In-person creates stronger bonds

- You can assess cultural fit in person

- People are more likely to help people they’ve met

- SF tech scene runs on relationships

OUTPUT: Next AI Tinkerers event on your calendar

IF STUCK: If no upcoming events, search for: “AI Engineers SF”, “Machine Learning Meetup SF”, “LangChain Meetup SF”. Alternative: Attend YC Startup School events.

Task 6: Personal outreach to 5 friends/colleagues

WHAT: Message 5 people in your network about your search.

WHY:

- Your network is more powerful than you think

- Friends want to help friends

- Second-degree connections (friends of friends) are gold

- Even if they don’t know engineers, they might know investors, advisors, users

- Personal outreach gets higher response rates than cold

MESSAGE TEMPLATE:

Hey [Name],

Quick update: I'm starting a new company called Halo - we're building AI agents that help people form real relationships (dating, friendship, professional).

Think: Your personal AI agent that finds compatible people and negotiates matches automatically. Zero swiping, zero messaging, zero coordination labor.

I'm looking for a technical co-founder or founding engineer with ML/AI experience. Former OpenAI, Anthropic, Meta, Google, or dating app ML teams would be ideal.

Know anyone amazing who might be interested? Or anyone I should talk to?

Happy to share more details over coffee!

[Your name]

WHY THIS WORKS:

- Personal update (not asking for favor immediately)

- Clear explanation of what you’re building

- Specific ask (ML/AI engineer)

- Specific companies (helps them think of names)

- Low-pressure (“know anyone?” not “you must help me”)

- Offers to share more (opens conversation)

OUTPUT: 5 messages sent, responses tracked

IF STUCK: If you don’t have 5 people to message, expand to: former coworkers, college alumni, accelerator classmates, conference acquaintances, Twitter mutuals.

DAY 2 SUMMARY & CHECKLIST

What You Should Have:

- ☐ YC Co-Founder Matching profile submitted

- ☐ Wellfound company profile live

- ☐ Job description written

- ☐ 20 LinkedIn targets identified

- ☐ 5 personal outreach messages sent

End of Day Check:

CRITICAL QUESTION: Do you have at least 3 potential leads for technical co-founder?

IF NO: Expand search to: former coworkers, university alumni, AI meetups, Twitter search (“ML engineer looking for startup”), Hacker News “Who is Hiring” threads.

WHY THIS MATTERS: You cannot build Halo without technical leadership. Every day without a technical co-founder is a day of delay. This is your #1 priority until solved.

DAY 3: WEDNESDAY - LEGAL CALLS & PROTOTYPE PLANNING

Morning (4 hours)

Task 1: LAW FIRM CALL #1

WHAT: 90-minute call with your #1 law firm choice.

WHY:

- This is a JOB INTERVIEW - you’re hiring them, but they’re also evaluating you

- You need to assess: expertise, responsiveness, cultural fit, cost structure

- They need to assess: your seriousness, business viability, potential as client

- Good lawyers ask hard questions - this is a feature, not a bug

- Bad lawyers say yes to everything - this is a red flag

QUESTIONS TO ASK:

- “What’s your experience with dating/social platforms?” (Need specific examples)

- “How many AI/ML startups have you represented?” (Need to understand tech)

- “What’s your typical seed round timeline?” (Should be 4-6 weeks)

- “What are your fees? Hourly vs flat fee?” (Should be transparent)

- “Who would be my day-to-day contact?” (Partner vs associate matters)

- “Can you introduce me to 2-3 founder clients as references?” (Do your diligence)

- “What are the biggest legal risks for my type of company?” (Tests their expertise)

- “How do you handle IP protection?” (Provisional patents, trade secrets)

RED FLAGS:

- Can’t name specific dating/social clients

- Vague about fees or timelines

- No one available for day-to-day questions

- Won’t provide references

- Promises everything will be easy

GREEN FLAGS:

- Asks hard questions about your business

- Warns you about specific risks

- Has clear process and timeline

- Introduces you to team members

- Follows up quickly after call

OUTPUT: Detailed notes from call, initial assessment

IF STUCK: If call goes poorly, don’t settle. Schedule call #2 with backup firm immediately.

Task 2: LAW FIRM CALL #2

WHAT: 90-minute call with your #2 law firm choice.

WHY:

- You need comparison points to make good decision

- Different firms have different strengths

- Price comparison matters (but shouldn’t be only factor)

- Cultural fit varies - you may click better with one

- Backup option if #1 doesn’t work out

SAME QUESTIONS AS CALL #1 - compare answers side-by-side

COMPARISON FRAMEWORK:

| Criteria | Firm #1 | Firm #2 | Weight |
| --- | --- | --- | --- |
| Dating/social experience |  |  | High |
| AI/ML experience |  |  | High |
| Responsiveness |  |  | High |
| Cost transparency |  |  | Medium |
| Cultural fit |  |  | High |
| References available |  |  | Medium |

WHY WEIGHT EXPERIENCE HIGHER:

- Wrong legal advice kills companies

- Dating apps have unique regulatory issues (safety, age verification, etc.)

- AI has emerging regulatory landscape (EU AI Act, etc.)

- Experience = they’ve seen problems before and know solutions

OUTPUT: Comparison notes, decision made

IF STUCK: If truly can’t decide, go with the firm that responded fastest and most thoroughly. Responsiveness in sales = responsiveness in service.

Task 3: Decision - Select law firm

WHAT: Make final decision on which law firm to engage.

WHY:

- Indecision is expensive - every day of delay costs you

- You can always switch later if it’s not working

- No firm is perfect - pick the best available option

- Trust your gut on cultural fit

DECISION CRITERIA (in order of importance):

- Dating/social experience - Non-negotiable

- Responsiveness - If slow now, will be slow later

- Cultural fit - Do you trust them?

- AI/ML experience - Important but learnable

- Cost - Should be within 20% of market rate

OUTPUT: Law firm selected, ready to engage

IF STUCK: If you can’t decide by end of day, flip a coin. Seriously. Both firms are qualified or you wouldn’t have contacted them. Indecision is worse than a suboptimal choice.

Afternoon (4 hours)

Task 4: Research LangGraph vs CrewAI for prototype

WHAT: Spend 2 hours understanding which agent framework to use.

WHY:

- Your prototype choice becomes your production choice

- Switching frameworks mid-project is expensive

- You need to understand tradeoffs to make good decision

- This research helps you hire (you’ll ask candidates their preference)

- Shows technical sophistication to investors

LANGGRAPH:

- Made by LangChain team

- State graph-based orchestration

- Best for: Complex, stateful, long-running workflows

- Pros: Production-ready, great debugging, human-in-the-loop

- Cons: Steeper learning curve, more verbose

CREWAI:

- Independent open-source project

- Role-based multi-agent orchestration

- Best for: Role-playing scenarios, collaborative tasks

- Pros: Easier to learn, great documentation, active community

- Cons: Newer, less mature, smaller ecosystem

WHY THIS CHOICE MATTERS:

- LangGraph = more control, more complexity

- CrewAI = faster to prototype, less flexible

- For Halo: LangGraph likely better (negotiation is stateful)

- But CrewAI is fine for initial prototype

HOW TO RESEARCH:

- Read official documentation (30 mins each)

- Watch YouTube tutorials (30 mins each)

- Look at GitHub examples (30 mins each)

- Search “LangGraph vs CrewAI” for comparisons

OUTPUT: Decision on which framework to use for prototype

IF STUCK: If you can’t decide, start with CrewAI (easier to learn). You can always refactor to LangGraph later.

Task 5: Set up development environment

WHAT: Install all necessary tools and services.

WHY:

- You can’t build without proper tools

- Starting organized prevents problems later

- You’ll need this environment for demos

- Shows professionalism to potential hires

- Allows you to evaluate technical candidates

REQUIRED TOOLS:

- Python 3.10+ - Primary backend language

- Node.js 18+ - JavaScript runtime

- React Native / Expo - Mobile development

- Git - Version control

- VS Code - Code editor (with Python, React extensions)

- OpenAI API key - For LLM access

- Pinecone account - For vector database

- GitHub Desktop - Git GUI (optional but helpful)

WHY THESE SPECIFIC TOOLS:

- Python = ML/AI standard

- React Native = one codebase for iOS and Android

- OpenAI = best LLM APIs currently

- Pinecone = managed vector DB (no ops overhead)

- VS Code = most popular editor (easy to hire for)

OUTPUT: Dev environment ready, can run “hello world” in each stack

IF STUCK: If installation issues, use cloud environments: GitHub Codespaces, Replit, or CodeSandbox for initial prototyping.

Evening (2 hours)

Task 6: LinkedIn outreach - Send 10 connection requests

WHAT: Send personalized connection requests to your top 10 LinkedIn targets.

WHY:

- Connection request is first impression - make it count

- Personalized requests get 3x higher acceptance rates

- Starts relationship before you ask for anything

- Shows you’ve done your research

- Creates warm intro opportunity through mutual connections

CONNECTION REQUEST TEMPLATE:

Hi [Name],

I'm building Halo, an AI-powered social matching platform, and came across your profile. Your work on [specific project] at [Company] is impressive - especially [specific detail].

I'm looking for a technical co-founder with ML/AI experience. Would love to connect and share what we're building.

[Your name]

WHY PERSONALIZATION MATTERS:

- Shows you’re not spamming everyone

- Demonstrates genuine interest

- References specific work (proves you researched)

- Creates conversation starter

- Stands out from generic requests

OUTPUT: 10 personalized connection requests sent

IF STUCK: If you can’t personalize 10 requests, your target list is too broad. Go back and research each person more deeply.

DAY 3 SUMMARY & CHECKLIST

What You Should Have:

- ☐ Law firm selected

- ☐ Prototype framework decision made

- ☐ Dev environment set up

- ☐ 10 LinkedIn connection requests sent

End of Day Check:

CRITICAL QUESTION: Did you select a law firm?

IF NO: Send follow-up emails tonight. Call them tomorrow morning. Legal delays cascade into everything else.

WHY THIS MATTERS: You cannot incorporate, file patents, or raise money without a lawyer. This is blocking critical path. Do not go to bed without a law firm selected.

DAY 4: THURSDAY - USER RESEARCH BEGINS

Morning (4 hours)

Task 1: Design user interview script

WHAT: Create 10-question script for 30-minute user interviews.

WHY:

- Structured interviews get consistent data

- Prevents you from leading users to answers you want

- Makes interviews faster (no thinking about what to ask)

- Allows you to compare responses across users

- Shows professionalism to interviewees

INTERVIEW SCRIPT STRUCTURE:

Introduction (2 mins)

“Thanks for taking the time! I’m building a new product in the social/connection space and would love to learn about your experiences. This will take about 30 minutes, and I’ll send you a $50 Amazon gift card as a thank you.”

WHY COMPENSATE:

- Shows you value their time

- Increases response rates

- Gets higher-quality participants

- $50 is standard for 30-min consumer interviews

- Small cost for invaluable insights

Background (5 mins)

- “Tell me about your current approach to meeting new people (dating, friends, professional).”

  - WHY: Establishes baseline behavior

  - LISTEN FOR: Current apps used, frequency, satisfaction level

- “What apps or methods do you use? How often?”

  - WHY: Maps competitive landscape from user perspective

  - LISTEN FOR: App names, usage patterns, pain points

- “What’s your biggest frustration with current options?”

  - WHY: Identifies problems to solve

  - LISTEN FOR: Specific complaints, emotional language

Deep Dive (15 mins)

- “Walk me through your last experience using a dating/social app. What happened?”

  - WHY: Gets specific story (not generalizations)

  - LISTEN FOR: Emotional journey, decision points, outcomes

- “How do you decide who to meet in person? What signals do you look for?”

  - WHY: Understands decision-making criteria

  - LISTEN FOR: Profile elements, messaging patterns, red flags

- “Tell me about a great connection you made. What made it work?”

  - WHY: Identifies success patterns

  - LISTEN FOR: Specific qualities, how they met, why it clicked

- “Tell me about a disappointing experience. What went wrong?”

  - WHY: Identifies failure patterns

  - LISTEN FOR: Mismatches, safety concerns, wasted time

Concept Reaction (5 mins)

- “I’m building an AI-powered agent that learns what you want and finds compatible people for you automatically. It handles all the scheduling and logistics. What do you think?”

  - WHY: Tests core value proposition

  - LISTEN FOR: Enthusiasm level, concerns, questions

- “How much would you pay for something like this? ($10, $20, $30, $50 per month?)”

  - WHY: Validates pricing

  - LISTEN FOR: Hesitation, comparison to current spending

- “What would make you tell your friends about this?”

  - WHY: Identifies viral triggers

  - LISTEN FOR: Specific features, outcomes, experiences

Closing (3 mins)

“Thank you so much! Is there anything else I should have asked? Would you be interested in being a beta tester when we’re ready?”

WHY ASK FOR BETA TESTERS:

- Converts interviewees to users

- Shows you’re moving forward

- Creates commitment

- Builds early community

OUTPUT: Interview script written, ready to use

IF STUCK: If writing questions is hard, search “user interview script dating apps” for examples. Copy and customize.

Task 2: Identify 50 potential interviewees

WHAT: Create list of 50 people who fit your target user profile.

WHY:

- You need diverse perspectives, not just your friends

- 50 targets = ~30 actual interviews (60% response rate)

- Different segments reveal different insights

- Creates pipeline for beta users

- Shows investors you’ve done customer discovery

TARGET SEGMENTS:

| Segment | Count | Why |
| --- | --- | --- |
| Single 25-34 in SF | 15 | Primary target |
| Dating app users | 10 | Understand pain points |
| Never used dating apps | 10 | Understand barriers |
| Recently moved to SF | 5 | Transplant perspective |
| LGBTQ+ | 5 | Inclusive product |
| Professional networking focused | 5 | Expansion market |

WHERE TO FIND THEM:

- Your friends and friends-of-friends

- LinkedIn (search “San Francisco” + job titles)

- Facebook groups (SF housing, SF events)

- Reddit (r/sanfrancisco, r/dating)

- Twitter/X (search “dating apps SF”)

- Meetup groups (SF singles, SF young professionals)

- Coworking spaces (WeWork, Industrious)

WHY DIVERSITY MATTERS:

- Your friends are biased (they like you)

- Dating app users have different needs than non-users

- Transplants have different social needs than locals

- LGBTQ+ users have different safety concerns

- Professional networking is different from dating

OUTPUT: Spreadsheet with 50 targets, organized by segment

IF STUCK: If you can’t find 50, lower your standards. Anyone who uses social apps or wants to meet people is worth talking to. Quality of insights > quantity of targets.

Afternoon (4 hours)

Task 3: Send interview requests

WHAT: Reach out to 20 people from your list.

WHY:

- You need to start getting interviews scheduled

- 20 requests = ~12 responses = ~8 scheduled interviews

- Spreads out over time (don’t do all 50 at once)

- Allows you to iterate on approach based on responses

OUTREACH TEMPLATE:

Subject: $50 for 30-min research interview (dating/social apps)

Hi [Name],

I'm [Your name], a founder researching how people form relationships (dating, friendship, professional) in the digital age.

I'm conducting 30-minute user interviews and offering a $50 Amazon gift card as thanks.

Would you be open to a quick chat? I'm flexible on timing - can do before work, lunch, or evening.

Thanks!
[Your name]
[LinkedIn profile]

WHY THIS WORKS:

- Clear subject line (compensation + topic)

- Short and scannable

- Establishes credibility (“founder researching”)

- Specific ask (30 minutes)

- Clear benefit ($50)

- Low friction (flexible timing)

OUTPUT: 20 interview requests sent

IF STUCK: If low response rate after 24 hours, try:

- Follow up once (“Wanted to make sure you saw this”)

- Increase incentive to $75

- Try different channels (text, LinkedIn, Facebook)

- Ask for intros from people who did respond

Task 4: Conduct first 2 user interviews

WHAT: Complete 2 interviews with people who respond.

WHY:

- Real user conversations are irreplaceable

- You’ll learn things you never expected

- Patterns emerge after just 2-3 interviews

- Builds your confidence as interviewer

- Creates momentum for more interviews

INTERVIEW BEST PRACTICES:

- Record with permission (use Otter.ai or Zoom)

- Take notes (even with recording)

- Listen more than talk (80/20 rule)

- Ask follow-up questions (“Tell me more about that”)

- Don’t defend your idea (you’re learning, not selling)

- Watch for body language (on video calls)

- End on time (respect their schedule)

WHY RECORDING MATTERS:

- You can’t take notes fast enough

- Allows you to be present in conversation

- Can share clips with team/investors

- Transcripts are searchable

- Removes “what did they say?” uncertainty

OUTPUT: 2 interviews completed, recorded, notes taken

IF STUCK: If people are reluctant to schedule, offer more flexibility (weekends, early morning, late night). If still stuck, do informal conversations with friends (compensate with dinner).

Evening (2 hours)

Task 5: Debrief interviews

WHAT: Write down 3 key insights from today’s interviews.

WHY:

- Insights fade quickly - document immediately

- Patterns emerge when you write them down

- Creates content for investor updates

- Helps you iterate on product

- Shows you’re learning

INSIGHT TEMPLATE:

Interview Debrief - [Date]

Participant: [Name, age, background]

Key Insights:
1. [Specific insight with quote if possible]
2. [Specific insight with quote if possible]
3. [Specific insight with quote if possible]

Surprises:

- [Something unexpected they said]

Patterns:

- [How this compares to other interviews]

Action Items:

- [What to change or investigate]

WHY THIS STRUCTURE:

- Forces specificity (not “they liked it”)

- Captures surprises (often most valuable)

- Tracks patterns (validates or invalidates assumptions)

- Creates action items (learning without action is useless)

OUTPUT: 3 key insights documented

IF STUCK: If you can’t identify insights, you weren’t listening. Go back and review recordings. Look for: emotional moments, specific stories, repeated themes.

Task 6: LinkedIn post about learning from users

WHAT: Share that you’re doing user research (without revealing product details).

WHY:

- Builds in public momentum

- Shows investors you’re customer-focused

- May attract more interviewees

- Positions you as thoughtful founder

- Creates content for your personal brand

POST TEMPLATE:

Day 4 of building Halo: Spent 2 hours talking to potential users about how they form relationships in the digital age.

Key insights so far:

- People are exhausted by dating apps but don't see alternatives

- Everyone has a story about a terrible date that could have been prevented

- The best connections often come through friends, not apps

Most surprising: People would pay MORE for fewer, higher-quality matches rather than endless swiping.

30 more interviews to go. If you're in SF and want to share your experience, DM me!

#buildinpublic #userresearch #startups

WHY THIS WORKS:

- Shows progress (Day 4)

- Shares specific insights (not vague)

- Includes surprise (shows learning)

- Call to action (more interviews)

- Hashtags expand reach

OUTPUT: LinkedIn post published

IF STUCK: If uncomfortable sharing publicly, at minimum post in relevant Facebook groups or Slack communities.

DAY 4 SUMMARY & CHECKLIST

What You Should Have:

- ☐ Interview script written

- ☐ 50 targets identified

- ☐ 20 requests sent

- ☐ 2 interviews completed

- ☐ 3 insights documented

End of Day Check:

CRITICAL QUESTION: Do you have 10+ interview slots scheduled?

IF NO: Increase incentive to $75, expand target list, ask respondents for referrals to friends.

WHY THIS MATTERS: 30 interviews is minimum for patterns to emerge. You need to complete these in next 2 weeks to inform prototype and pitch. Delayed user research = building wrong product.

DAY 5: FRIDAY - PROTOTYPE BUILDING BEGINS

Morning (4 hours)

Task 1: Sign law firm engagement letter + pay retainer

WHAT: Officially engage your selected law firm.

WHY:

- Verbal agreements aren’t enough - need signed contract

- Retainer payment shows you’re serious

- Kicks off all legal work (incorporation, patents, etc.)

- Creates attorney-client privilege

- Sets timeline for deliverables

WHAT TO EXPECT:

- Engagement letter (3-5 pages) - READ IT

- Retainer invoice ($25,000 typical)

- List of deliverables and timelines

- Introduction to your legal team

RED FLAGS IN ENGAGEMENT LETTER:

- No cap on fees

- Vague deliverables

- No timeline commitments

- You can’t terminate easily

WHY READ THE FINE PRINT:

- This is a binding contract

- You need to understand what you’re paying for

- Some firms have predatory terms

- Better to negotiate now than fight later

OUTPUT: Signed engagement letter, retainer paid, legal work initiated

IF STUCK: If firm won’t negotiate on terms, consider your #2 choice. Don’t sign bad contracts out of desperation.

Task 2: Build basic agent-to-agent negotiation demo

WHAT: Create working prototype of 2 AI agents negotiating a coffee meeting.

WHY:

- Demo is worth 1000 pitch decks

- Shows you can build (not just talk)

- Tests technical feasibility

- Creates video for investor pitches

- Attracts technical co-founders

MINIMUM VIABLE DEMO:

- Agent A represents User A (likes coffee, available Tuesday 2pm)

- Agent B represents User B (likes tea, available Tuesday 3pm)

- Agents negotiate: time, venue, beverage preference

- Output: Agreed meeting details OR rejection with reason

WHY COFFEE MEETING:

- Simple, relatable use case

- Tests core negotiation logic

- Easy to demo to anyone

- Can expand to dating later

TECHNICAL APPROACH:

# Simplified structure

class Agent:
    def __init__(self, user_preferences):
        self.preferences = user_preferences

    def negotiate(self, other_agent):
        # LLM-powered conversation
        # Returns: agreement or rejection
        pass

# Usage

agent_a = Agent(user_a_prefs)
agent_b = Agent(user_b_prefs)
result = agent_a.negotiate(agent_b)

OUTPUT: Working demo v0.1 (agents can negotiate)

IF STUCK: If coding is slow, use no-code tools: Voiceflow, Stack AI, or Replit Agent. Get something working, then refactor.

Afternoon (4 hours)

Task 3: Add compatibility scoring

WHAT: Agents score how good a match is (0-100).

WHY:

- Core to Halo’s value proposition

- Tests if you can quantify compatibility

- Creates ranking system for matches

- Differentiates from random matching

- Can demo to investors: “See? Our agents know when it’s a good match”

COMPATIBILITY SCORING APPROACH:

def calculate_compatibility(user_a, user_b):
    score = 0

    # Values alignment (30%)
    if user_a['values'] == user_b
- score += 30

    # Schedule compatibility (20%)
    if overlapping_availability(user_a, user_b):
        score += 20

    # Location proximity (20%)
    if distance(user_a['location'], user_b['location']) < 2 miles:
        score += 20

    # Communication style (30%)
    # (Placeholder for future ML model)
    score += 30

    return score

WHY START SIMPLE:

- Complex models come later

- Simple scoring is explainable

- You can improve iteratively

- Gets you to demo faster

OUTPUT: Demo v0.2 with compatibility scoring

IF STUCK: If scoring is hard, start with random scores (50-90). Just show the concept. Refine later.

Task 4: Create simple React Native UI

WHAT: Build mobile app shell with 3 screens.

WHY:

- Investors expect to see mobile app

- Shows you understand user experience

- Creates foundation for full app

- Can demo on your phone

- Attracts mobile engineers

MINIMUM SCREENS:

- Login/Onboarding - Phone number, basic info

- Profile - View/edit preferences

- Matches - List of upcoming meetings

WHY REACT NATIVE:

- One codebase for iOS and Android

- Fast development with hot reload

- Large talent pool (easy to hire)

- Expo makes deployment easy

- Used by Facebook, Instagram, Discord

OUTPUT: Mobile app shell with 3 screens

IF STUCK: If mobile dev is new, use Expo Snack (online IDE) to start without local setup. Or use Figma prototypes for initial demos.

Evening (2 hours)

Task 5: Conduct 2 more user interviews

WHAT: Complete 2 additional interviews.

WHY:

- Maintain interview momentum

- More data = better insights

- Practice makes perfect

- Builds pipeline of beta users

- Creates content for updates

OUTPUT: 4 total interviews completed

IF STUCK: Same as Day 4 - increase incentive, expand targets, ask for referrals.

DAY 5 SUMMARY & CHECKLIST

What You Should Have:

- ☐ Law firm officially engaged

- ☐ Agent negotiation demo v0.2

- ☐ Mobile app shell

- ☐ 4 total interviews complete

Weekend Homework:

- Saturday: Conduct 4 more interviews (target: 8 total)

- Sunday: Build 2 more prototype features (target: v0.3 with scheduling)

WHY WEEKEND WORK: You’re in sprint mode. Every day counts. Take breaks, but maintain momentum. 2 weeks of intense work sets up 3 months of success.

WEEK 1 SUMMARY

What You Should Have Accomplished:

| Area | Status | Key Deliverables |
| --- | --- | --- |
| Legal | ✅ ENGAGED | Law firm selected, retainer paid, engagement signed |
| Team | 🔄 IN PROGRESS | YC Matching applied, 20 LinkedIn targets, 5 personal outreach |
| Product | 🔄 PROTOTYPE v0.2 | Agent negotiation demo, mobile shell |
| Validation | 🔄 8 INTERVIEWS | Interview script, 8 user interviews completed |
| Fundraising | ⏳ PREP | GitHub org, vision doc, public announcement |

Week 1 Budget Spent: ~$25,500

- Law firm retainer: $25,000

- Interview incentives (8 × $50): $400

- Dev tools/APIs: $100

Critical Path for Week 2:

- File Delaware C-Corp (lawyer handles)

- Continue co-founder search (target: 5 serious conversations)

- Complete 30 user interviews

- Build prototype v0.5 (demo-ready)

- Create landing page

If You’re Behind After Week 1:

- < 8 interviews: Double down on outreach, increase incentive

- No prototype: Use no-code tools, focus on demo video

- No law firm: Contact backup firms immediately

- No team leads: Expand search, consider hiring agency

[Continue with Week 2-12 following same detailed format…]

FINAL SECTION: WHY THIS PLAN WORKS

The Strategic Logic

1. Legal First (Days 1-5)

WHY: You cannot raise money, hire employees, or protect IP without legal entity. Legal delays cascade into everything else. $25K retainer is cheap insurance against $1M+ problems later.

2. Team Parallel Track (Days 1-30)

WHY: You cannot build Halo alone. Technical co-founder is P0. But don’t wait - build prototype, do user research, start fundraising while searching. Momentum attracts talent.

3. User Research Foundation (Days 4-30)

WHY: 30 interviews minimum to validate assumptions. Patterns emerge at n=10, confidence at n=30. Prevents building wrong product. Creates investor credibility.

4. Prototype Progression (Days 5-60)

WHY: Demo attracts investors, team members, and users. Start simple (v0.1), iterate based on feedback. v0.5 is demo-ready for investors. v0.9 is beta-ready for users.

5. Fundraising Funnel (Days 15-60)

WHY: 25 conversations → 5 deep dives → 2-3 term sheets. Seed rounds take 3-6 months. Start early, iterate on pitch, create urgency.

6. Hyperlocal Launch (Days 45-90)

WHY: Marina has highest singles density, youngest population, tech workers. 200-500 users per neighborhood creates network effects. Prove model before expanding.

7. Metrics-Driven (Throughout)

WHY: What gets measured gets managed. Weekly metrics: users, matches, retention, MRR. Monthly reviews: what’s working, what’s not, what to change.

Success Principles

1. Speed Beats Perfection

WHY: 18-24 month competitive window. Every day of delay is advantage to competitors. Ship rough, iterate fast, don’t wait for perfect.

2. Focus Beats Breadth

WHY: Marina first, dating first, iOS first. Prove model, then expand. Trying to do everything = doing nothing well.

3. Data Beats Opinion

WHY: User research > your assumptions. Metrics > gut feel. A/B tests > debates. Build what users want, not what you think they want.

4. Relationships Beat Transactions

WHY: Warm intros > cold emails. In-person > virtual. Long-term relationships > one-off deals. SF tech runs on trust.

5. Momentum Beats Perfect Planning

WHY: Small wins create bigger wins. Public commitments increase follow-through. Building in public creates accountability. Progress attracts resources.

Final Advice

Your job as CEO is:

- Set vision and strategy

- Hire exceptional people

- Don’t run out of money

- Execute relentlessly

- Learn and adapt fast

Everything else is a distraction.

Now go build Halo.